## SME
ID | As a | I Would like to | So that | Sprint | Days | Member
SM001 | SME | Login using Associate ID and Password. Implement logout as well | I Can Access Home Page | 1 | 5 | Teja
SM002 | SME | View Dashboard with Recent Courses, # of Courses Contributed, Current Active Batches, History on # of Contributions in a Chart, Profile Card with Name, Image, Rating | I can have a big picture about the various status on courses and batches | 1 | 8 | Pawan
SM003 | SME | View my profile | I can see my credentials and the ratings/badges. | 1 | 3 | Manish C
SM004 | SME | View all courses sorted by relavance | I can view the list of courses available.
SM005 | SME | Search courses on the based course name or skill name. After entering 3 characters course cards should appear in the bottom | I can view the course details | 1 | 5 | Mohit Jain
SM006 | SME | create a new template course with title, description, | I can manage a particular course template | 1 | 3 | Manish J
SM007 | SME | link course to a batch | I can assign the copy of template course to different batches.
SM007 | SME | Modify existing course template details | I can edit a particular course template | 1 | 3 | Selvi
SM009 | SME | Modify course details of a specific batch | I can edit course of a specific batch
SM010 | SME | create learning project with title, content with images for reference | I can manage a particular learning project | 1 | 8 | Rishika
SM011 | SME | modify learning project | I can edit a particular learning project | 1 | 8 | Subham
SM012 | SME | assign learning project to a course template | I can assign learning projects to a template course | 1
SM013 | SME | assign learning project to a specific batch | I can manage projects of a particular batch
SM014 | SME | Search skill based on name, preview skill details and add the skill to a course | add existing skill to a course | 1 | 8 | Deepak
SM015 | SME | Create a new skill in a course template | Create a new skill under a course with skill name, objective and description related to skill entity in template | 1 | 5 | Sonu
SM017 | SME | Modify an existing skill template | modify skill under a course with skill name, objective and description related to skill entity in template | 1 | 5 | Aneesh
SM015a | SME | Add pre-requisite to a skill | I can add pre-requisites for a skill | 1 | 2 | Phani
SM015b | SME | Delete pre-requisite from a skill | I can remove pre-requisites for a skill | 1 | 2 | Phani
SM015c | SME | Add software required with version number | I can add software required for a skill | 1 | 2 | Rajat
SM015d | SME | Delete software required from a skill | I can remove software required for a skill | 1 | 2 | Rajat
SM018 | SME | List of all problem statements inside a skill template | View all problem statements under a particular skill | 1
SM019 | SME | Modify an existing skill for a particular batch course if the skill has not been completed | Modify skill name, objective, pre- requisites, software requirements and description related to skill entity in template
SM020 | SME | Create a new skill in a batch course if the batch is still active and the skill can be added only to the incomplete section of the batch | Add a new skill for a particular batch
SM021 | SME | Copy an existing skill to batch course from a course template if the batch is still active and the skill can be added only to the incomplete section of the batch | Use this modified skill for another batch
SM022 | SME | List of all problem statements inside a skill for a batch | View all problem statements under a particular skill in skill template
SM023 | SME | Copy modified skill from batch course to a course template | Use modified skill for any other batches
SM024 | SME | Create a problem statement within a skill. A problem statement will have title, content, Input, output, sequence and duration | I can create a new problem statement of a particular skill using tinyMCE | 1 | 8 | Shivani
SM025 | SME | Modify problem statement's title, content, input, output, sequence and duration of a skill | I can modify a problem statement | 1 | 8 | Garvit
SM026 | SME | Give sequence to each problem statement | I can increase the complexity of the course by time | 1
SM027 | SME | Copy a problem statement from a particular skill | I can create a copy and reuse it after modifying for another skill
SM028 | SME | Add a problem statement to a particular course that is already assigned to batch | I can add a new problem statement to a already on going course
SM029 | SME | Modify a problem statement that is not yet touched of a particular course that is already assigned to a batch | I can modify the problem statement
SM030 | SME | Search problem statements from template, show preview and attach the problem statement with skill | I can reuse existing problem statement | 1 | 8 | JJ
SM031 | SME | Copy a problem statement from template | I can reuse the problem statement in other courses | 1
SM032 | SME | Create a Learning Objective with Code, Description and Sequence for a problem statement | I can manage learning objective in a particular Problem Statement in the template | 1 | 5 | Aritra
SM033 | SME | Modify a Learning Objective in the template | I can edit the Learning Objective in the template | 1 | 5 | Shubhendu
SM034 | SME | Remove a Learning Objective in the template | I can remove the Learning Objective in the template | 1 | 3 | Ashish
SM035 | SME | Update newly created template Learning Objective to the course assigned to a particular batch | I can add the Learing Objective to the course, if the batch has not completed that particular problem statement
SM036 | SME | Update newly Modified template Learning Objective to the course assigned to a particular batch | I can update the Learning Objective of the course,if the batch has not completed that particular learning ojective
SM037 | SME | Create a Learning Objective of a course assigned to a particular batch | I can add the Learning Objective of the course assigned to that Batch
SM038 | SME | Modify a Learning Objective of a course assigned to a particular batch | I can edit the Learning Objective of the course assigned to that Batch
SM039 | SME | Remove a Learning Objective of a course assigned to a particular batch | I can remove the Learning Objective of the course assigned to that Batch
SM040 | SME | Create activity within a learning objective with activity name, description and type (Article, Video, Classroom Discussion, Learning Snippet. Image, Facilitator Lecture, Group Activity) | I can manage activities of a particular learning objective | 1
SM0401 | SME | Create/Modify/Delete activity for a learning objective with activity type Article | I can manage activities of a particular learning objective | 1 | 5 | Thomas
SM0402 | SME | Create/Modify/Delete activity for a learning objective with activity type Video | I can manage activities of a particular learning objective | 1 | 5 | Gagan
SM0404 | SME | Create/Modify/Delete activity for a learning objective with activity type Learning Snippet | I can manage activities of a particular learning objective | 1 | 5 | Bhatta
SM0406 | SME | Create/Modify/Delete activity for a learning objective with activity type Facilitator Lecture | I can manage activities of a particular learning objective | 1 | 5 | Abhishek
SM0407 | SME | Create/Modify/Delete activity for a learning objective with activity type Group Activity | I can manage activities of a particular learning objective | 1 | 5 | Arun
SM043 | SME | Add activity to existing batch course | I can add an activity to existing batch course
SM044 | SME | Edit activity of existing batch course if no learner of a batch has marked it complete | I can change activity from batch course without interfering with the batch progress
SM045 | SME | Delete activity of existing batch course if no learner of a batch has marked it complete | I can remove activity from batch course without interfering with the batch progress
SM046 | SME | Create a new Check for a course with title, description, duration, input, expected result and check type (practice or final) | I can manage Check of a particular skill using tinyMCE | 1 | 5 | abesh
SM047 | SME | Find a Check and attach to a course template schedule as final/practice | I can reuse existing Practice Check | 1 | 8 | Divya
SM048 | SME | Modify a Check | I can edit a check | 1 | 5 | Rishabh
SM049 | SME | Create / Delete score criteria for a Check with title and weightage. The total weightage should be 100. | I can manage score criteria | 1 | 5 | surbhi
SM052 | SME | Find a Check based on batch | I can manage a particular check for a batch
SM053 | SME | Modify the check content based on batch | I can edit a check content attached to a batch
SM054 | SME | View Course Duration | I know the number days it requires to complete the course | 1
SM055 | SME | Change course status to "Change in Progress" when change is made in Skill, Problem Statement, Learning Objective or Criteria | I ensure incomplete course content is not assigned to a batch. | 1
SM056 | SME | Change course status to "Ready for Batch Assignment" when all changes in the course is incorporated | I can enable the course to be assigned to a batch. | 1
SM057 | SME | Change made in course, skill, problem statement or check should ask for the summary of change made | anybody can view the history of who made what changes | 1
SM058 | SME | View Suggestions from the facilitator | I can view suggestions from facilitator
SM059 | SME | Report Bug to Admin | I can report a bug or an error.
SM060 | SME | Logout | I can logout from Application

## User_Stories
ID | As a | I Would like to | So that
LE001 | Learner | Signup for the first time with the fields - Cognizant Email Id, Associate Id, Name and password. | I can be a valid and authenticated user for the system.
LE002 | Learner | have an authentication link on my cognizant Email Id | on clicking the link I can be authenticated for the system
LE003 | Learner | Login using Email Id or Associate Id and Password | I Can Access Home Page
LE004 | Learner
LE005 | Learner | Access the Course assigned to me. | I can refer to the course content and the topics in it.
LE006 | Learner | have list of activities as part of a skill with the learning objectives | on completion of an activity I can mark it as completed.
LE007 | Learner | Have a skill completed after all the activities provided are completed | I can have access to the next skill.
LE008 | Learner | Add remarks on a topic | If the topic is unclear to a learner, steps can be taken by the facilitator.
LE009 | Learner | access Check Point after completion of certain skills | So that I can have Practice check and Final Check
LE010 | Learner | View My Batch Progress | I can view the progress marked by facilitator
LE011 | Learner | View Completed Modules | I can check my Completed Courses
LE012 | Learner | View weekly goals | I can have an idea and overview of all the topics to be covered in the coming week.
LE013 | Learner | View My Progress | I can track my progress in all courses
LE014 | Learner | View facilitator message | I can have common messages for my batch from the facilitator.
LE015 | Learner | View My Schedule | I can see my course schedule
LE016 | Learner | View Case Studies in Particular Topic | I can choose one case study from available list
LE017 | Learner | Give Rating to SME and Facilitator | it will help to assign badges to respective SME and Facilitator
LE018 | Learner | View my ratings given by Facilitator | I will get to know my ratings
LE019 | Learner | Get notified when course is updated | I can be able know when my course is updated
LE020 | Learner | Report a bug or an error. | Report Bug to Admin
LE021 | Learner | Logout | I can logout from the application
LE022 | Learner
FA001 | Facilitator | Login using Email and Password | I can Access Home Page
FA002 | Facilitator | View Facilitator Dashboard
FA003 | Facilitator | View List of Batches | I can see all the batches assigned to me
FA004 | Facilitator | View Batch Progress(Training) | I can track progress of a Batch in a course they're being trained
FA005 | Facilitator | Add Weekly Goal(Batch) | I can set a weekly goal for a Batch
FA006 | Facilitator | Edit Weekly Goal | I can edit a weekly goal for the batch
FA007 | Facilitator | Remove Weekly Goal | I can remove the weekly goal for a batch
FA008 | Facilitator | View Batch Schedule (Training) | I can view daywise schedule of a batch and their module objectives for each day
FA009 | Facilitator | Update Batch Progress (Training) | I can mark Skills completed and update Batch Progress
FA010 | Facilitator | Enable Practice Check | The Learners Can see practice check created by sme
FA011 | Facilitator | Enable Final check | The Learners Can see final check created by sme
FA012 | Facilitator | Give rating to learner for practice check | The learner gets to know about his performance in practice and final check
FA013 | Facilitator | Give rating to BO | The facilitator can express his feelings about BO
FA014 | Facilitator | View list of Learners in a Batch | I can view learners mapped to me
FA015 | Facilitator | View Learner Progress (Self Learning) | I can track self learning progress of Learners of my Batch
FA016 | Facilitator | View My ratings and cummulative badge | I will be able to see where I stands
FA017 | Facilitator | Suggestion to SME | I can Suggest Course Related Content to SME
FA018 | Facilitator | Report Bug to Admin | I can report a bug or an error.
FA019 | Facilitator | Logout | I can logout from the application
BO 001 | Batch Owner | View my own profile | I can see my credentials and profiloe data.
BO 002 | Batch Owner | Search for User based Email ID/ Assoc. ID/ Assoc. Name | I Can View User, add a learner to batch and attach/detach a facilitator to a batch
BO 003 | Batch Owner | Attach/Detach a facilitator to a batch | the facilitator can be mapped to a batch
BO 004 | Batch Owner | Attach/Detach multiple facilitators to a batch | Multiple facilitators can manage single batch
BO 005 | Batch Owner | Search for a particular batch using batch ID under my supervision | I can edit batch details, add/detach learners to a batch by searching his associate ID, view learners already added to a batch, view course of a batch, view progress of a batch, add/detach facilitator to a batch
BO 006 | Batch Owner | Add Multiple Learners to a Batch by importing Excel Sheet Data | Those Learners can view the courses assigned to that batch
BO 007 | Batch Owner | View active batches under me | I can edit batch details, add/detach learners to a batch by searching his associate ID, view learners already added to a batch, view course of a batch, view progress of a batch, add/detach facilitator to a batch
BO 008 | Batch Owner | Add a learner to a batch | The learner can view the course assigned to the batch
BO 009 | Batch Owner | Detach a learner from a batch | the learners progress won't affect the Batch Progress and he can see completed Modules only
BO 010 | Batch Owner | View all facilitators associated with the batch | see the details such as start of training and end of training of the batch with that facilitator
BO 011 | Batch Owner | Give ratings to a batch under my supervision | It will add to the batch's ratings.
BO 012 | Batch Owner | Edit batch details | I can change batch release date
BO 013 | Batch Owner | View batch progress | Track and monitor the training program of a batch
BO 014 | Batch Owner | View learners associated with a batch | I can check and monitor their individual progress
BO 015 | Batch Owner | View course schedule and structure of a batch | I can know what are the technologies the learners are going to learn
BO 016 | Batch Owner | Deactivate a learner under my supervision | I can remove a learner who has resigned or been terminated
BO 017 | Batch Owner | Activate a deactivated learner under my supervision | I can reactivate a learner who has been deactivated by mistake
BO 018 | Batch Owner | Mark a batch as complete | The batch won't be displayed in my active batches list
BO 019 | Batch Owner | Accept/Reject Leave of Facilitator | Facilitator can manage day accordingly
BO 020 | Batch Owner | Report Bug to Admin | I can report a bug or an error.
BO 021 | Batch Owner | adding microcredentials
BO 022 | Batch Owner | Logout | I can logout of the application
SM 001 | SME | Login using Email and Password | I Can Access Home Page
SM 002 | SME | View Dashboard | I can view the count of Published Courses and Drafted Courses
SM 003 | SME | View my profile | I can see my credentials and the ratings/badges.
SM 004 | SME | View all courses sorted by relavance | I can view the list of courses available.
SM 005 | SME | Search courses on the basis of name | I can view the course details
SM 006 | SME | Create a new course template with course name and pre-requisites | I can manage a particular course template
SM 007 | SME | Modify existing course template details | I can edit a particular course template
SM 007A | SME | Modify course details of a specific batch | I can edit course of a specific batch
SM 008 | SME | Add a skill of a course template with skill name, description,duration and software requirements | I can search for a particular skill, add a new skills in a particular course template
| SME | Find a skill and attach to a course template | I can reuse existing skill content
SM 009 | SME | Modify existing skill | I can edit a particular skill.
SM 010 | SME | Create a problem statement within a skill with name and description | I can manage problem statements of a particular skill using tinyMCE
SM 011 | SME | Modify problem statement within a skill | I can edit a problem statement
SM 012 | SME | Create a learning objective with description within a problem statement | I can manage learning objectives in a particular problem statement.
SM 013 | SME | Modify a learning objective | I can edit a learning objective
SM 014 | SME | Create a learning project within a course template with name and description. | I can manage learning project of a course template using tinyMCE
SM 015 | SME | Modify a learning project | I can edit a learning project
SM 016 | SME | Create a Practice Check within a skill with name and description. | I can manage Practice Check of a particular skill using tinyMCE
SM 017 | SME | Modify a Practice Check | I can edit a practice check
SM 018 | SME | Create a Final Check within a skill with name and description. | I can manage Final Check of a particular skill using tinyMCE
SM 019 | SME | Modify a Final Check | I can edit a Final Check
SM 020 | SME | Draft a course | I can temporarily save the contents of a course template
SM 021 | SME | Publish a course | I can publish content and send notification to Learners Mapped to it once it is ready
SM 022 | SME | Modify a published course by searching a course name | I can edit a published course or skills by making a copy of the original one and editing(based on the completion of the course or skills by all batchs tagged to the course or skills) the course as a draft.
SM 023 | SME | Draft a copied published course | I can temporarily save the contents of the course.
SM 024 | SME | Publish a copied published course | I can publish the course in place of the published course/create a new version of the course or skill and send notification to Learners Mapped to it once it is ready.
SM 025 | SME | View Suggestions from the facilitator | I can view suggestions from facilitator
SM 026 | SME | Report Bug to Admin | I can report a bug or an error.
SM 027 | SME | Logout | I can logout from Application
AD 001 | Admin | Login using Email and Password | I Can Access Home Page
AD 002 | Admin | View Dashboard | I can view the count of courses, facilitators, SMEs, Learners, Bos
AD 003 | Admin | View List of Users, Courses and Batches | I can get the details of users, courses and Batches
AD 004 | Admin | Search for User based Email ID/ Assoc. ID/ Assoc. Name | I Can View User and change their Roles (Admin, SME, Facilitator, B.O), Activate/Deactivate the User
AD 005 | Admin | Deactivate a User | I can prevent user to login into system
AD 006 | Admin | Activate a Deactivated User | I have an option to revert back the deactivated status
AD 007 | Admin | Change role of an User | I can change the role of the user (Admin, SME, Facilitator, B.O. or Learner)
AD 008 | Admin | Create a Batch with Batch ID, Batch Name, Start Date and Course | I can manage the execution of a Batch
AD 009 | Admin | Search for batch based on Batch ID/ Batch Name | I can find a batch to manage it
AD 010 | Admin | View Details of a particular Batch | I can know about Facilitator, BO, Learners, Course and Progress
AD 011 | Admin | Assign multiple learners to a batch | They can be mapped to Particular Batch
AD 012 | Admin | Add a single learner to a batch | I can add a learner to a batch at a later point of time
AD 013 | Admin | Detach learner from a batch | I can remove a learner from a batch
AD 014 | Admin | Add Facilitator to a batch | the training can be managed
AD 015 | Admin | Detach Facilitator from a batch | I can remove facilitator from a batch
AD 016 | Admin | Attach B.O. to a Batch | the B.O. can be mapped to a batch
AD 017 | Admin | Detach B.O. from a Batch | I can remvoe B.O. from a Batch
AD 018 | Admin | Remove Batch (only if batch does not contain any data) | I Can Remove Batch which is wrongly created
AD 019 | Admin | Search a Course with Course Name | I can see the courses which are in the system
AD 020 | Admin | View the entire course content | I can get to know the contents of a course
AD 021 | Admin | View All Bugs reported by Users | I can fix those bugs
AD 022 | Admin | Logout | I can logout of the application